## Functional Flow Changes
# | Source | Module | Issue / Title | Why Needs Client Discussion | Priority | Type
DEFECTS & BUGS
4 | Portal Issues | Cities | Delete icon deactivates city instead of deleting it | Business decision needed: should cities be permanently deleted (hard delete) or just deactivated (soft delete)? Current UI has separate Active/Inactive toggle, so delete icon behavior needs to be redefined. | High | Functional
K1 | Kalpesh File | Login | No sign-up option — new users cannot self-register | Business decision: is self-registration intended? Or should only admins create accounts? If self-registration is needed, a full registration + email verification flow is required. | High | Functional
K7 | Kalpesh File | Staff | Inactive staff members can still access all features (security gap) | Critical security issue. When admin marks staff as Inactive, their active session must be revoked immediately. Requires backend session invalidation strategy — needs spec confirmation before implementation. | Critical | Security
24 | Portal Issues | Dashboard | Daily Summary trigger button does not send emails to recipients | Possibly a backend email service misconfiguration or cron/trigger timing issue. Need to confirm: is email expected to be immediate or delayed? Any backend env config to verify? | High | Functional
31 | Portal Issues | Staff | Staff user does not receive email notification when account is created by Admin | Email notification on account creation is not implemented. Requires decision on email content/template and whether to send plain credentials or a set-password link. | Medium | Functional
K12 | Kalpesh File | Energy Report | Email not sent after report generation (API returns emailSent: false) | Email service (SendGrid) may be misconfigured or hitting an error silently. Need to verify env vars and whether this is a config issue or a feature that was never fully implemented. | High | Functional
K13 | Kalpesh File | Utility Data Upload | Total kBTU field requires manual entry instead of auto-calculating from Electric + Gas | Need client to confirm the exact kBTU conversion formula to use. Standard: (Electric kWh × 3.412) + (Gas therms × 100) = kBTU. Please confirm if this formula applies. | High | Functional
K14 | Kalpesh File | Reports | All generated reports always show 0 kBTU savings | Savings calculation logic is not working. Need baseline data spec from client: What is the baseline period? How is savings % calculated? Without the business logic spec, we cannot fix the calculation. | Critical | Functional
ENHANCEMENT REQUESTS
14 | Portal Issues | All Modules | No sorting functionality available on any data table (Cities, Buildings, Recipients, Staff) | New feature requiring significant development. Need client to prioritize which tables need sorting first and confirm desired sort behavior (client-side vs server-side for large datasets). | Medium | Enhancement
15 | Portal Issues | All Modules | No filtering functionality available across the site | New feature. Need to define: which fields to filter on, per module. E.g., Cities: by state/status; Buildings: by city/status; Recipients: by building/status. Client to provide filter spec. | Medium | Enhancement
16 | Portal Issues | Buildings | Status column in Buildings exists but there is no way to change it (Active/Inactive) | Design decision: do we add an activate/deactivate action to buildings (similar to cities)? Or should the column be removed if not actionable? Client to decide. | Medium | Enhancement
19 | Portal Issues | Compliance | No filter for Message History section (by Delivered / Pending / Uploaded) | New feature. Scope and priority to be confirmed by client. | Medium | Enhancement
22 | Portal Issues | Login | Forgot Password option missing on all login screens (Admin, Building, Staff) | Requires new password reset flow: forgot password form → email with reset link → reset password page. Needs email template and token system. Client to confirm priority. | High | Enhancement
I1 | Kalpesh Improvements | Dashboard | Smart Default Filters: default dashboards to last 24h with 24h/7d/30d quick toggle | New feature. Needs scope confirmation and which data feeds support time-based filtering. | Medium | Enhancement
I2 | Kalpesh Improvements | Cities | City Risk Scoring: calculated Cold Risk Score per city (temp history + alert frequency) | Significant new feature. Need business rules for scoring formula before development. | Low | Enhancement
I3 | Kalpesh Improvements | Cities | Pre-configured Cold Cities: preloaded Northeast city dataset with default alert configs | Requires curated dataset and default config values from client. Who defines the defaults? | Low | Enhancement
I4 | Kalpesh Improvements | Cities | Bulk Upload: CSV/Excel import for adding multiple cities at once | New feature. Need file format spec and field mapping from client. | Medium | Enhancement
I5 | Kalpesh Improvements | Cities / Buildings | Inline Editing: edit table rows directly without navigating to separate page | Major UX change affecting all table modules. Significant development effort — client to prioritize. | Low | Enhancement
I6 | Kalpesh Improvements | Buildings | Building Health Score: composite indicator combining alerts, compliance %, response time | Significant new feature. Need scoring formula and threshold definitions from client. | Low | Enhancement
I7 | Kalpesh Improvements | Compliance | Auto Escalation Rules: e.g., if compliance < 20% for 3 days → notify admin | New feature requiring rule engine. Need rule definitions and escalation paths from client. | Low | Enhancement
I8 | Kalpesh Improvements | Alerts | Smart Alert Triggering: only fire if temp change persists for X minutes | Business logic change to alert engine. Need the X-minute threshold and persistence logic confirmed. | Low | Enhancement
I9 | Kalpesh Improvements | Alert Logs | Alert Deduplication: group repeated alerts for same building into single thread with count | New grouping feature. Need UX spec: does expanding the group show individual alerts? | Low | Enhancement
I10 | Kalpesh Improvements | Cities | Region-based Grouping: filter/group cities by region or state | New feature. Need region taxonomy/mapping from client. | Medium | Enhancement
I11 | Kalpesh Improvements | All Modules | Global Search: universal search bar for cities, buildings, staff, messages | Significant new feature touching all modules. Client to confirm scope and priority. | Low | Enhancement