## Issue Status
# | Source | Issue Type | Priority | Title | Status
1 | Portal Issues | UI/UX Bug | High | City search dropdown remains visible and blocks UI after clearing input in 'Search' field under 'Create New City' popup, on 'Cities' page. | Done
2 | Portal Issues | Functional | High | City search suggestion returns incorrect results in first search attempt, but corrects after retyping the city name in 'Search' field under 'Create New City' popup, on 'Cities' page. | Done
3 | Portal Issues | UI/UX Bug | Medium | Duplicate city options appearing in search city dropdown under 'Create New City' popup, on 'Cities' page. | Done
6 | Portal Issues | UI/UX Bug | Medium | User is not redirected to 'Cities' page after updating city details from 'Edit city configuration' page. | Done
7 | Portal Issues | Functional | Medium | User is able to duplicate city entries with identical name, NWS grid, and configuration data on 'Cities' page. | Done
9 | Portal Issues | UI/UX Bug | Medium | Background page remains scrollable and causes scroll glitch after selecting city in 'Add Building' popup on 'Buildings' page. | Done
10 | Portal Issues | UX | Medium | Status' column shows multiple states simultaneously (Active + Paused) causing unclear/confusing behavior on 'Buildings' page. | Done
11 | Portal Issues | UI/UX Bug | Medium | Validation error for missing email/phone appears on 'Recipients' list page instead of 'Add Recipient' popup. | Done
12 | Portal Issues | UI/UX Bug | Medium | No validation appearing after entering invalid mobile number under 'Add/Edit Recipient' popup on 'Recipients' page. | Done
13 | Portal Issues | UI/UX Bug | Medium | No success message appears after updating records on 'Buildings, Recipients, and Staff' pages. | Done
17 | Portal Issues | UI/UX Bug | Medium | 'Select a City' option from filter dropdown resets page to empty state despite being a non-actionable/default option on 'Templates' page. | Done
20 | Portal Issues | Functional | High | Generic error displayed when generating duplicate report instead of proper validation message, on 'Energy & Reports' page. | Done
21 | Portal Issues | Enhancement | Medium | 'User Role' (Admin/Staff) is not visually distinguished/highlighted on the header, reducing visibility and clarity. | Done
23 | Portal Issues | UI/UX Bug | Medium | No validation when no building is selected under 'Add Recipient' popup despite default checkbox pre-selected like 1st Building name on 'Recipient' page. | Done
25 | Portal Issues | UI | Medium | Header layout breaks at 100% zoom causing overlap between 'User Role' label and navigation tabs ('Energy/Messages') with screen size 1265 × 559. | Done
26 | Portal Issues | Functional | High | 'Sent At' detail displays incorrect default timestamp '01/01/1970, 05:30:00' on 'Messages' page after triggering action, on 'Dashboard' page. | Done
27 | Portal Issues | UI | Medium | Incorrect success message grammar message appear after uploading the file under 'Upload compliance photo or BMS record' popup. | Done
28 | Portal Issues | Enhancement | Medium | Missing navigation option after file upload completion, under 'Upload compliance photo or BMS record' popup. | Done
30 | Portal Issues | Functional | Medium | 'Copy Link' option is not working under 'Recent reports' section on 'Energy' page, across the website only in Safari browser. | Done
34 | Portal Issues | UI | Medium | Show an info message when no details available under 'Utility consumption history' section, on 'Energy & Reports' page. | Done
K2 | Kalpesh - Defects | Validation | Critical | Validation message missing from the modal (Add City). | Done
K3 | Kalpesh - Defects | Redirection | High | The user stays on the edit page after clicking on Save Changes button. | Done
K5 | Kalpesh - Defects | UI/UX | Low | The line break added for the other cells in the table by clicking on 'Paused' icon. | Done
K6 | Kalpesh - Defects | UI/UX | Low | The building name dropdown shows cropped from right side. | Done
K10 | Kalpesh - Defects | Functional | High | System allows creation of duplicate buildings with same name and address. | Done
K11 | Kalpesh - Defects | Functional / Validation | High | Year field accepts invalid and non-standard values without validation. | Done
I16 | Kalpesh - Improvements | Enhancement | - | Edit recipient – Replace browser default validation with custom inline validation messages styled consistently with the application UI. | Done
I17 | Kalpesh - Improvements | Enhancement | - | Input Validation & UX – Add input constraints and UI controls for Year field (4-digit numeric, min/max range, inline validation). | Done
8 | Portal Issues | UI/UX Bug | Medium | Unnecessary empty space appears below the 'City Statistics' section on 'Dashboard' page, affecting layout consistency. | Done
18 | Portal Issues | Functional | High | 'Delete' action neither deletes the template nor shows any success/error message on 'Templates' page. | Done
29 | Portal Issues | Functional | High | 'View' button is not available under 'Recent Uploads' section on Building Portal. | Done
32 | Portal Issues | Functional | High | User unable to view all reports generated by Staff (Only one report displayed). | Done
K7 | Kalpesh - Defects | Security | Critical | Inactive staff member able to access the features. | Done
K8 | Kalpesh - Defects | Functional | High | An Admin not able to delete the staff member. | Done
K9 | Kalpesh - Defects | Functional | High | The delete action not functional for the Templates. | Done
K13 | Kalpesh - Defects | Functional | High | Total kBTU should be auto-calculated instead of manual entry. | Done
I19 | Kalpesh - Improvements | Enhancement | - | UI / User Interaction – Change cursor to a hand pointer when hovering over interactive elements such as list items, buttons, dropdowns. | Done
I13 | Kalpesh - Improvements | Enhancement | - | Retry Failed Messages – Provide Retry button for failed messages with error reason. | Done
I14 | Kalpesh - Improvements | Enhancement | - | Smart Empty States – Show guided messages like 'No cities added yet – Click here to add or upload CSV'. | Done
I15 | Kalpesh - Improvements | Enhancement | - | UI Consistency – Standardize text formatting (e.g., auto Title Case for building name and address). | Done
I18 | Kalpesh - Improvements | Enhancement | - | User Feedback & Notification – Provide clear feedback on email status after report generation (success/fail/retry). | Done
5 | Portal Issues | Functional | High | User is not able to search city name under 'Edit city configuration' section, on 'Cities' page. | Done
4 | Portal Issues | Functional | Medium | 'Delete' action deactivates city instead of deleting, causing confusion with existing status control on 'Cities' page. | Done
14 | Portal Issues | Enhancement | Medium | No sorting functionality available across the data tables (Cities, Buildings, Recipients, Staff) for better data management, across the website. | Not Started
15 | Portal Issues | Enhancement | Medium | No filtering functionality available across the website to refine and view specific data. | Not Started
16 | Portal Issues | Enhancement | Medium | 'Status' column available in 'Buildings' module without any option to modify or manage status (Active/Inactive) on 'Buildings' page. | Done
19 | Portal Issues | Enhancement | Medium | No filter options are available to segregate messages based on their status in 'Message History' section, on 'Compliance' page. | Not Started
22 | Portal Issues | Enhancement | Medium | 'Forgot Password' option is missing across all login screens (Admin, Building, Staff), blocking account recovery. | Done
24 | Portal Issues | Functional | High | 'Daily Summary' trigger button from Dashboard does not send emails to 'Recipients' even after complete setup of creation (City -> Building -> Recipient) flow. | Done
31 | Portal Issues | Functional | Medium | Staff user not receiving email notification after account creation by Admin. | Not Started
33 | Portal Issues | UI | Medium | Alignment issue occurring in generated report PDF file. | Done
K1 | Kalpesh - Defects | Functional | High | The new user not able to register. | Not Started
K4 | Kalpesh - Defects | Functional | High | The delete icon performing 'Deactivate' function. | Done
K12 | Kalpesh - Defects | Functional | High | Energy report not sent via email even after providing valid email address. | Done
K14 | Kalpesh - Defects | Functional | High | Generated reports always show 0 kBTU savings. | Done
I1 | Kalpesh - Improvements | Enhancement | - | Smart Default Filters – Default all dashboards and reports to last 24 hours or current day, with quick toggle options (24h / 7d / 30d). | Not Started
I2 | Kalpesh - Improvements | Enhancement | - | City Risk Scoring – Add a calculated 'Cold Risk Score' per city using historical temperature data + alert frequency. | Not Started
I3 | Kalpesh - Improvements | Enhancement | - | Pre-configured Cold Cities – Provide a preloaded dataset of Northeast cold cities with default alert configs. | Not Started
I4 | Kalpesh - Improvements | Enhancement | - | Bulk Upload for Cities – Enable CSV/Excel upload to add multiple cities at once. | Not Started
I5 | Kalpesh - Improvements | Enhancement | - | Inline Editing – Allow editing city/building details directly within table rows instead of navigating to separate pages. | Not Started
I6 | Kalpesh - Improvements | Enhancement | - | Building Health Score – Introduce a composite score combining alert frequency, compliance %, and response time. | Not Started
I7 | Kalpesh - Improvements | Enhancement | - | Auto Escalation Rules – Configure rules such as 'If compliance < 20% for 3 days → notify admin + escalate to staff'. | Not Started
I8 | Kalpesh - Improvements | Enhancement | - | Smart Alert Triggering – Add logic to trigger alerts only if temperature change persists for X minutes. | Not Started
I9 | Kalpesh - Improvements | Enhancement | - | Alert Deduplication – Group repeated alerts for the same building/city into a single thread with count. | Not Started
I10 | Kalpesh - Improvements | Enhancement | - | Region-based Grouping – Allow grouping/filtering cities by region (Northeast, Midwest, etc.) or state. | Not Started
I11 | Kalpesh - Improvements | Enhancement | - | Global Search – Implement a universal search bar that can find cities, buildings, staff, messages instantly. | Not Started
I12 | Kalpesh - Improvements | Enhancement | - | One-click Compliance Upload – Add direct 'Upload Photo' button inside alert notification or message (no navigation needed). | Not Started